PB-03

Playbook: SOC 2 Type 2 readiness in 90 days

How to get a small organisation ready for a SOC 2 Type 2 examination in about ninety days, then run the observation period the auditor samples.

| Document ID | PB-03 |
| --- | --- |
| Title | Playbook: SOC 2 Type 2 readiness in 90 days |
| Type | Playbook |
| Framework | Cross-framework |
| Requirements served | SOC 2 CC4.1; SOC 2 CC1.2 |
| Owner (role) | Information Security Manager |
| Approver (role) | Chief Executive Officer |
| Classification | Internal |
| Version | 1.0 (template) |
| Effective date | [Date] |
| Review | Annual |

Revision history

| Version | Date | Change | Approved by |
| --- | --- | --- | --- |
| 1.0 | [Date] | First issue from the kit template | [Role] |

# 1. Purpose

This playbook takes a team with little formal structure to the point where a SOC 2 Type 2 examination can begin. It explains the difference between design and operation, the ninety days of preparation, and the observation period that follows, which is where the real evidence is made.

# 2. What SOC 2 is, in one paragraph

SOC 2 is a report, not a certificate, written by a licensed accounting firm against the Trust Services Criteria. A Type 1 report says the controls are suitably designed at a point in time. A Type 2 report says they also operated over a period, usually three to twelve months. Security is always in scope; availability, confidentiality, processing integrity and privacy are added only if you commit to them. The report reader, often a customer's security team, drives the scope.

# 3. Roles

| Role | In this effort |
| --- | --- |
| Project owner | Runs the readiness work and the evidence calendar. |
| Chief Executive Officer | Owns commitments, approves policies, chairs governance. |
| Engineering and operations leads | Produce technical evidence and fix technical gaps. |
| People lead | Produces onboarding, training and background-check evidence. |
| Auditor | The accounting firm, engaged once design is in place. |

# 4. The phases

4.1 Scope and categories (about days 0 to 10). Decide which Trust Services categories the report covers, based on what customers ask for. Define the system: the product, the people, the locations, the technology and the supporting corporate systems. Draft the system description with SOC-TPL-01.

4.2 Gap assessment (about days 10 to 25). Fill the readiness checklist (SOC-REG-03) and map every criterion to a control in the matrix (SOC-REG-01). Each gap becomes a corrective action in GOV-REG-03 with an owner and a date.

4.3 Remediation (about days 25 to 60). Close the gaps. Adopt the policies and procedures the criteria need, turn on the technical controls, and make sure each control has a named owner and a place where its evidence lands.

4.4 Evidence collection begins (about days 60 to 90). Start the evidence calendar (SOC-REG-02). From here on, every recurring control must produce evidence for every occurrence. This is the habit the Type 2 period depends on.

4.5 The observation period (three to twelve months). The controls operate and produce evidence continuously. Access reviews, vulnerability scans, change approvals, backups and training all run on their cadence, and each occurrence is kept. A Type 1 report at the ninety-day mark is an optional milestone that proves design while the period runs.

4.6 Audit fieldwork and report. The auditor samples the period, holds walkthroughs, inspects evidence and writes the report. Gaps found here are expensive, which is why the evidence calendar matters more than any single document.

# 5. The evidence calendar is the backbone

The single most useful tool is the recurring-events calendar (SOC-REG-02): the daily, weekly, monthly, quarterly and annual control events, each with an owner and the evidence it produces. A common monthly discipline is to spot-check one-twelfth of the controls, so that the whole set is reviewed once a year outside the audit.

# 6. What good evidence looks like

Evidence is a system export, a ticket, an approval or a dated screenshot, named as PB-09 describes, showing who did what and when. A blank template is not evidence. An empty register is not evidence. Back-dating is never evidence. If a control did not run, record that it did not and open a corrective action.

# 7. Common gaps to expect

Governance and HR evidence (board minutes, job descriptions, background checks, training records), a complete system description, a populated vendor inventory with assurance, and proof that recurring technical controls actually ran. Start these early; they take the longest to produce.

# 8. Related documents

SOC-GDE-01 SOC 2 in plain words

SOC-TPL-01 System description template

SOC-REG-01 Trust Services Criteria control matrix

SOC-REG-02 Evidence calendar

SOC-REG-03 Readiness checklist

PB-08 Running a readiness assessment

PB-09 Evidence management

This document is a template from an open documentation kit. Replace every item in square brackets, remove what does not apply, and have the approver sign it before use. A template is not evidence of compliance.